# Sprint 3 Plan: SilkSync

Product Name: SilkSync

Team Name: BevGo!

Sprint Completion Date: [e.g., 2/25/2025]

### Goal

Finish implementing itinerary features and enable core HSR (High-Speed Rail) social travel features, allowing users to search train numbers with real-time departure times and pricing, check in to a specific train journey, and set a social intent to discover compatible travel companions. By the end of the sprint, users should be able to find a train, join a trip context, and express their social preferences.

### Task Listing

Tasks are estimated in ideal hours (focused work without interruption), aiming for 6 hours per task.

#### User Story 3.1: HSR Train Search (Priority: High – 13 pts)

"As a traveler, I want to search for HSR train numbers so that I can view departure times and current ticket pricing."

- Task 3.1.1: Research/select HSR data source and configure API access (4 hrs)

- Task 3.1.2: Design backend schema and implement train search endpoint (6 hrs)

- Task 3.1.3: Build and integrate Train Search UI with error handling (6 hrs)

- Task 3.1.4: Unit test search logic and API parsing (3 hrs)

  - Total for User Story 3.1: 19 hours

#### User Story 3.2: Train Check-In (8 pts – High Priority)

"As a solo traveler, I want to check in to my train number so that I can find others on the same journey."

- Task 3.2.1: Design Check-In schema and implement backend endpoint (6 hrs)

- Task 3.2.2: Build Check-In UI and integrate with backend (5 hrs)

- Task 3.2.3: Implement traveler list query and display co-travelers (6 hrs)

  - Total: 17 hours

#### User Story 3.3: Social Intent (8 pts – High Priority)

"As a user, I want to set my Social Intent to find like-minded companions."

- Task 3.3.1: Extend user profile schema to support Social Intent (3 hrs)

- Task 3.3.2: Build Social Intent selection UI and persistence logic (5 hrs)

- Task 3.3.3: Integrate intent display into traveler list (3 hrs)

  - Total: 11 hours

### Team Roles & Assignments

Each member is assigned a primary role and an initial task to ensure immediate progress.

| Team Member | Role(s) for Sprint 1 | Initial Task Assignment |
| --- | --- | --- |
| Emerson Wang | Frontend Developer | 3.1.3 (Train Search UI) |
| Kevin Zhang | Backend Developer | 3.1.2 (Search Endpoint) |
| Jason Pan | Integration Engineer | 3.1.1 (HSR API Setup) |
| Kiana Penner | QA / Backend Developer | 3.3.2 (Intent UI + Testing) |

### Scrum Logistics

- Initial burnup chart:

| Day | Date | Total Scope (Ideal Hours) | Completed Work (Cumulative Hours) | Notes / Milestones |
| --- | --- | --- | --- | --- |
| 0 | 2/11 | 47 | 0 | Sprint Start |
| 1 | 2/12 | 47 | 3 | Social Intent Schema Started |
| 2 | 2/13 | 47 | 6 | HSR API research & selection |
| 7 | 2/18 | 47 | 16 | UI Complete & Search endpoint basic implementation |
| 8 | 2/19 | 47 | 22 | Check in schema & backend endpoint begins |
| 10 | 2/21 | 47 | 29 | Traveler list query + logic |
| 13 | 2/24 | 47 | 32 | Testing complete, continue reviewing bugs and finish implementations |
| 14 | 2/25 | 47 | 35 | Sprint End |

- Initial scrum board: https://arima.atlassian.net/jira/software/projects/SCRUM/boards/1/backlog?atlOrigin=eyJpIjoiOTBlNmNiMGJiNjRjNGE4MmFkOTE0MTJjYWY4M2YzYjAiLCJwIjoiaiJ9&cloudId=96395332-7726-482b-b402-fda0335b24e0

- Scrum Times: Tuesday 7:00-7:45 PM, Saturday 7:00-7:30 PM, Sunday 7:00PM - 7:30 PM, Wednesday, 12  - 12:55 PM (Lab time visit arranged with TA for Fridays)