# Sprint 1 Plan: SilkSync

Product Name: SilkSync

Team Name: BevGo!

Sprint Completion Date: [e.g., 1/28/2025]

Revision: 1.0 (1/14/2025)

### Goal

Establish the core mobile infrastructure, including user authentication, the dual-map coordinate-correction bridge, and the real-time currency exchange engine. Users will be able to launch the app and view their location, as well as view China-specific mapping. Users should input USD amounts to see real-time currency conversions for travel budgeting.

### Task Listing

Tasks are estimated in ideal hours (focused work without interruption), aiming for $\le 6$ hours per task.

#### User Story 1.1: Account Core

"As a user, I want to authenticate via email or social login so that my travel preferences and history are saved."

- Task 1.1.1: Research and select Auth provider (Firebase Auth or Auth0) (2 hrs)

- Task 1.1.2: Configure backend database schema for User profiles (PostgreSQL) (4 hrs)

- Task 1.1.3: Implement Login/Sign-up UI screens in mobile framework (5 hrs)

- Task 1.1.4: Integrate frontend with Auth API and handle JWT session tokens (6 hrs)

- Task 1.1.5: Unit test login flow and error handling for invalid credentials (3 hrs)

- Total for User Story 1.1: 20 hours

#### User Story 1.2: Dual-Map Bridge

"As an international traveler, I want my map to switch to Amap when I enter China to ensure navigation accuracy."

- Task 1.2.1: Obtain API keys for Mapbox (Global) and Amap/Gaode (China) (1 hr)

- Task 1.2.2: Implement GPS geolocation service to detect "Current Country" (3 hrs)

- Task 1.2.3: Build the "Map Bridge" component that hot-swaps SDKs based on location (6 hrs)

- Task 1.2.4: Resolve the "GCJ-02" coordinate offset for Chinese mapping (Spike/Research) (4 hrs)

- Task 1.2.5: UI Implementation: Toggle for manual map override (2 hrs)

  - Total for User Story 1.2: 16 hours

#### User Story 1.3: FX Engine

"As a planner, I want to input USD and see CNY conversions for accurate budget planning."

- Task 1.3.1: Select and integrate a real-time Exchange Rate API (e.g., Frankfurter or Fixer) (3 hrs)

- Task 1.3.2: Develop backend service to fetch and cache daily USD/CNY rates (4 hrs)

- Task 1.3.3: Build a reusable Budget-Input UI component with live conversion (4 hrs)

- Task 1.3.4: Create unit tests for conversion logic (handling decimal precision) (2 hrs)

- Total for User Story 1.3: 13 hours

### Team Roles & Assignments

Each member is assigned a primary role and an initial task to ensure immediate progress.

| Team Member | Role(s) for Sprint 1 | Initial Task Assignment |
| --- | --- | --- |
| Emerson Wang | Frontend Developer | 1.1: Task 1.1.2 (Login UI) |
| Kevin Zhang | Backend Developer | 1.1: Task 1.1.3 (DB Schema) |
| Jason Pan | Integration Engineer | 1.2: Task 1.2.3 (Map Bridge) |
| Kiana Penner | QA / Developer | 1.3: Task 1.3.1 (API Integration) |

### Scrum Logistics

- Initial burnup chart:

| Day | Date | Total Scope (Ideal Hours) | Completed Work (Cumulative Hours) | Notes / Milestones |
| --- | --- | --- | --- | --- |
| 0 | 1/14 | 49 | 0 | Sprint Start |
| 1 | 1/15 | 49 | 2 | Auth Provider Research |
| 2 | 1/16 | 49 | 4 | Map API Key procurement |
| 7 | 1/21 | 49 | 16 | Login UI Implementation |
| 8 | 1/22 | 49 | 20 | Auth Integration & JWT handling |
| 10 | 1/24 | 49 | 27 | GPS Location detection |
| 13 | 1/27 | 49 | 30 | Home Screen Template basics and Currency Exchange API |
| 14 | 1/28 | 49 | 33 | Sprint End: US 1.1 & 1.3 Done |

- Initial scrum board: https://arima.atlassian.net/jira/software/projects/SCRUM/boards/1/backlog?atlOrigin=eyJpIjoiOTBlNmNiMGJiNjRjNGE4MmFkOTE0MTJjYWY4M2YzYjAiLCJwIjoiaiJ9&cloudId=96395332-7726-482b-b402-fda0335b24e0

- Scrum Times: Tuesday 7:00-7:45 PM, Saturday 7:00-7:30 PM, Sunday 7:00PM - 7:30 PM, Wednesday, 12  - 12:55 PM (Lab time visit arranged with TA for Fridays)